## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 467 | 74 | 22 | 371 | 196.5 | 174.5
001 | Project Start and End Dates | 2022-01-10 | 2022-04-16 | 96
002 | Get structure mockup completed | 2022-02-09 | 2022-02-11 | 2 |  |  | 4 | 4 | 0 | Ideas | Diagram | Ray, Sawyer | Complete
003 | Install Past group Projecy | 2022-02-12 | 2022-02-18 | 6 |  |  | 1 | 1 | 0 | Project Deliverables | Downloaded System | All | Complete
004 | Get software to work as intended | 2022-02-19 | 2022-02-23 | 4 |  |  | 5 | 5 | 0 | Downloaded System | Working system with minimal errors | All | Complete
005 | Analyze Features | 2022-02-23 | 2022-03-01 | 6 |  |  | 3 | 3 | 0 | System Features | Understanding of what features are and ideas | All | Complete
006 | Consider new Features | 2022-03-01 | 2022-03-04 | 3 |  |  | 3 | 3 | 0 | Ideas and System features | Plausible and neccesary additional features | J, Robert, Saywer | Complete
007 | Have features Approved | 2022-03-04 | 2022-03-04 | 0 |  |  | 1.5 | 1.5 | 0 | Plausible Features | Approval from professor | All | Complete
008 | Update Database so new features match | 2022-03-04 | 2022-03-06 | 2 |  |  | 5 | 0 | 5 | Old database | Updated database | J, Ray, Jacqueline | In Progress
009 | Break Admin/login page code down to remake with Java FX | 2022-02-23 | 2022-03-01 | 6 |  |  | 5 | 5 | 0 | Old group's code | Java conversion | Sawyer, Robert | Complete
009 | Make commandline code connect to database | 2022-03-01 | 2022-03-06 | 5 |  |  | 7 | 4 | 3 | Database and commandline interface(not connected) | Connected interface | Ray, Sawyer | In Progress
010 | Create Test cases for admin and test | 2022-03-04 | 2022-03-06 | 2 |  |  | 5 | 1 | 4 | code for admin page and an idea of what it should be able to do | Test cases and results of tests | J, Jacqueline | In Progress
011 | Make admin page work with Swing | 2022-03-04 | 2022-03-10 | 6 |  |  | 6 | 6 | 0 | Old groups code/basics of our code | Working admin system code | Sawyer, Ray | Complete
012 | Break down views | 2022-03-10 | 2022-03-14 | 4 |  |  | 4 | 4 | 0 | Old groups web code | Understanding of what needs to be done | Saywer, Ray, Robert | Complete
013 | Code Receptionist View | 2022-03-14 | 2022-03-16 | 2 |  |  | 5 | 3 | 2 | Draft of code | Working code | Robert, Sawyer | In Progress
014 | Test Recptionist View | 2022-03-14 | 2022-03-17 | 3 |  |  | 5 | 4 | 1 | Database and code | Database connectivity | All | In Progress
018 | Break down doctor Imageing code | 2022-03-20 | 2022-03-24 | 4 |  |  | 3 | 3 | 0 | Draft of code from old system | Working code in swing | All | Complete
019 | Connect test cases from database for image system and test | 2022-03-21 | 2022-03-25 | 4 |  |  | 5 | 3 | 2 | Code and databse information | Connected system | All | In Progress
020 | Make the Doctor and radiologist view pages work through the command line with JavaFX | 2022-03-17 | 2022-03-24 | 7 |  |  | 7 | 6 | 1 | Draft of code from old system | Working Code in Swing | All | In Progress
021 | Connect database Doctor and radiologist views and test | 2022-03-21 | 2022-03-25 | 4 |  |  | 4 | 4 | 0 | Code and databse information | Databse connectivity | All | Complete
022 | Break down patient page | 2022-03-21 | 2022-03-25 | 4 |  |  | 3 | 3 | 0 | Draft of code from old system | Working code in Swing | All | Complete
023 | Make the patient info page work through command line | 2022-03-21 | 2022-03-25 | 4 |  |  | 5 | 4 | 1 | Code and databse information | Database connectivty | All | In Progress
024 | Connect database for Patient view and test | 2022-03-21 | 2022-03-25 | 4 |  |  | 4 | 2 | 2 | Code and database | Connection | All | In Progress
025 | Test whole system with no additional features | 2022-03-25 | 2022-03-25 | 0 |  |  | 6 | 4 | 2 | Code | Tests that work! | All | In Progress
026 | Code Billing System | 2022-03-25 | 2022-04-04 | 10 |  |  | 5 | 0 | 5 | Work up for functionality | Working billing system | All | In Progress
027 | Creating database entries for billings and connect database to system | 2022-03-25 | 2022-04-04 | 10 |  |  | 5 | 0 | 5 | Idea of what is needed in system | Usable database and connect to billing system | All | In Progress
028 | Connect patient information between different views | 2022-03-25 | 2022-04-04 | 10 |  |  | 5 | 0 | 5 | Work up for functionality | working patient info | All | In Progress
029 | Code specific error pages | 2022-03-25 | 2022-04-04 | 10 |  |  | 5 | 0 | 5 | Idea for error things | working error pages | All | In Progress
026 | Plan GUI based off of teams structure -jframe and JavaFX | 2022-02-14 | 2022-03-06 | 20 |  |  | 7 | 7 | 0 | Past groups GUI | Plan for new GUI | All | Complete
027 | Code GUI for login | 2022-02-20 | 2022-03-04 | 12 |  |  | 6 | 6 | 0 | Plan for GUI and past groups GUI | Working GUI for login | Robert | Complete
028 | Code GUIS for different views | 2022-03-06 | 2022-03-26 | 20 |  |  | 15 | 0 | 15 | Plan for GUI and past groups GUI | Working GUI for all views | Robert, J, Jacqueline | In Progress
029 | Integrate GUI and commandline code | 2022-02-28 | 2022-03-30 | 30 |  |  | 20 | 10 | 10 | Working GUI and internal code | System that works together | All | In Progress
030 | Test all features | 2022-03-30 | 2022-04-05 | 6 |  |  | 6 | 0 | 6 | Complete Code and testing cases | Debugged system | All | In Progress
031 | Have Code ready to be tested by other groups | 2022-01-10 | 2022-04-05 | 85 |  |  | 162.5 | 100 | 62.5 | Past system | Our system working completely | All | In Progress
032 | Test other groups' project | 2022-04-06 | 2022-04-12 | 6 |  |  | 4 | 0 | 4 | Other group's projects | Test cases and results of tests | All | In Progress
033 | Create Document with the result of testing the other groups project | 2022-04-12 | 2022-04-13 | 1 |  |  | 3 | 0 | 3 | Testing cases | Docementation of testing | J, Jacqueline | In Progress
034 | Create List of features, scenarios and user stories | 2022-04-07 | 2022-04-08 | 1 |  |  | 3 | 0 | 3 | Features ready to go | Documentation of features | Sawyer, Robert | In Progress
035 | Document all test cases and results(defects and resolutions) | 2022-03-04 | 2022-04-08 | 35 |  |  | 5 | 0 | 5 | Test cases | Documentation of test cases and results | J, Jaqueline | In Progress
036 | Make graphical and textual description of software architecture | 2022-04-08 | 2022-04-09 | 1 |  |  | 2 | 0 | 2 | Working RIS system | Document with description of code | All | In Progress
037 | Create Installation Instruction Document | 2022-04-07 | 2022-04-12 | 5 |  |  | 6 | 0 | 6 | Understanding of how to install our code | Documentation of installation | Ray,Sawyer | In Progress
038 | Create list of all tools used in development process | 2022-04-08 | 2022-04-09 | 1 |  |  | 1 | 0 | 1 | Tools used for development | Documentation of tools used in development | All | In Progress
039 | Create a user manual (should include which system our system is based off of) | 2022-04-07 | 2022-04-16 | 9 |  |  | 6 | 0 | 6 | Understanding of how our RIS system works | User Manual | J, Ray, Jaqueline | In Progress
040 | Create Document containing lessons learned | 2022-04-12 | 2022-04-16 | 4 |  |  | 2 | 0 | 2 | Understanding of project process | Documentation of lessons learned | All | In Progress
041 | Create Document containing links to all other deliverables | 2022-04-12 | 2022-04-16 | 4 |  |  | 1 | 0 | 1 | All deliverables and working system | sheet with all deliverables connects | All | In Progress
042 | Create Powerpoint presentation | 2022-04-07 | 2022-04-16 | 9 |  |  | 5 | 0 | 5 | All deliverables and working system | Professional powepoint | All | In Progress
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()